PhD ROADMAP

Exercise 1: A Working Plan

Evolutionary annotation of Alzheimer’s disease risk loci

What this is. A day-by-day plan for your first two weeks, a thematic plan for the next two months, and milestone goals for the next two years — built directly from your two documents: the population-genetics primer and the Lucas Exercise 1 protocol (v3.1).

Assumptions. You are working on this roughly full-time on weekdays; weekends are light/catch-up. Adjust freely — the sequence matters more than the exact calendar. Confirm scope and the locus source with your PI in week one.

# Contents

# Standing habits (all two years)

Four disciplines the protocol keeps returning to. Build them now; they are what make the work defensible.

- Keep a lab notebook / project README. Every decision, every allele correction, every threshold, dated. “A caveat with containment is a strength.”

- Work reproducibly. Scripts, not manual copy-paste from web tools. Version your master table. Anyone should be able to re-run your pipeline.

- Separate the four layers of interpretation. Observation → robust observation → evolutionary model → biological hypothesis. Never let them blur in your notes or figures.

- Run the reviewer reflex. Every time you see a signal, ask first: “what non-selective process — demography, drift, ascertainment, or an allele error could have produced this?” A clean negative beats an over-interpreted positive.

The one idea under everything Selection is never observed directly. It is inferred as a deviation from what drift and population history alone would produce. Every method you learn is either a way to measure that deviation, or a way to prove it isn’t an artifact.

# The next two weeks — day by day

Goal: get the conceptual scaffolding in place, read the three core papers, install your tools, and produce a clean, versioned master table for the 10 pilot loci. This mirrors weeks 1–2 of the protocol timeline.

Do this on Day 1, before anything else Start the data-access paperwork. Talk to your PI and sponsored-programs office about an eRA Commons account and a dbGaP Data Access Request, and register interest in the All of Us Researcher Workbench. Approvals — not analysis — are the rate-limiting step of year one. Everything else this week can proceed in parallel while the queue moves.

## Week 1 — Foundations and orientation

Day 1 (Mon)  —  Setup + kick off data access

- Start the data-access paperwork (see box above) — eRA Commons, dbGaP, All of Us.

- Set up your workspace: reference manager (Zotero), a versioned project folder, and a lab notebook / README file.

- Read primer Ch. 1–2 (Logic of Population Genetics; How Selection Leaves Footprints). Do the check-your-understanding questions.

Day 2 (Tue)  —  The data views and the statistics

- Read primer Ch. 3–4 (Two Views of the Data; The Statistics, Decoded).

- Build the reference table the protocol asks for: statistic → footprint it reads → timescale it detects. Keep it one page.

- Install your toolkit: bcftools, PLINK2, a Python env with scikit-allel, and R with LDlinkR.

Day 3 (Wed)  —  Demography and the hard cases

- Read primer Ch. 5–6 (Demography: the great impostor; Recent and polygenic selection) plus Ch. 7 and the glossary.

- Write a half-page in your own words: why demography mimics selection, and the two escape routes (matched genome-wide background; explicit demographic modelling).

Day 4 (Thu)  —  Paper 1 — Vitti, Grossman & Sabeti (2013)

- Read for the map, not the algebra. This is your catalogue of footprints and statistics.

- Extend your statistic → footprint → timescale table as you go. When it’s complete, it’s your working reference for the whole project.

Day 5 (Fri)  —  Finish Vitti + first PI check-in + test the data

- Finish Vitti. Meet your PI/mentor: confirm the locus source (Bellenguez 2026 supplement) and the pilot scope.

- Locate the 1000 Genomes high-coverage data and run bcftools on one chromosome as a smoke test (chr19 is a good choice — it carries APOE).

Weekend (light): skim Coop’s open-access lecture notes for any shaky concept (drift, LD, coalescent). Read Williams (1957) on pleiotropy and senescence — short, and central to your framing.

## Week 2 — The methods papers and your first master table

Day 6 (Mon)  —  Paper 2 — Cheng & Steinrücken (2024), pass 1

- Read for concepts: the coalescent, the demography-vs-selection problem, and why a selection scan needs a demographic null.

- Pull the Bellenguez 2026 supplementary tables and get familiar with their columns.

Day 7 (Tue)  —  Cheng & Steinrücken pass 2 + build the table schema

- Second pass for tool names you’ll actually use: Relate, tsinfer/tsdate, dadi, PSMC/MSMC, S/HIC.

- Set up your master locus table schema from protocol Section 18 (locus_id, lead_snp, variant_id_GRCh38, risk_allele_harmonized, source_GWAS, phenotype_class, candidate_gene, consequence, qc_flags).

Day 8 (Wed)  —  Paper 3 — Mills & Mathieson (2022) + extract pilot loci

- Read for failure modes: the height-selection retraction, polygenic selection, stratification, why ancient DNA matters.

- Extract the 10 pilot loci (APOE/TOMM40, BIN1, CLU, ABCA7, TREM2, CR1, MS4A, SORL1, INPP5D, HLA) into the master table.

Day 9 (Thu)  —  Allele harmonization

- Harmonize each pilot locus: rsID → chr:pos:REF:ALT in GRCh38 via Ensembl/VEP; record effect allele and risk allele from the source.

- Flag the traps: palindromic (A/T, C/G) SNPs, multi-allelic sites, indels, merged/split rsIDs. Flag rather than guess.

Day 10 (Fri)  —  Audit, freeze v1, checkpoint

- Finish and audit the 10-locus harmonization twice; compare reported effect-allele frequency against 1000G EUR.

- Freeze master table v1 with a version number and an audit note.

- Two-week checkpoint: core reading done, toolkit working, clean pilot master table in hand. Write a short progress note for your PI.

Weekend (light): rest. Optional: Shi & Holtzman (2018) on innate immunity and Alzheimer’s (APOE, TREM2) — good bridge to your disease-biology side.

# The next two months — mid-term goals

Goal: turn the pilot into a working, reproducible pipeline, complete all analyses on the 10 pilot loci, then scale to all 91. This is weeks 3–8 of the protocol timeline, plus a scale-up phase.

| Weeks | Focus | Deliverable |
| --- | --- | --- |
| 3 | 1000 Genomes allele frequencies for pilot loci (then all 91 if the pipeline holds). Compute risk-allele AF per super-population, ΔAF, rare/missingness flags. | Frequency table with ΔAF columns; first plots. |
| 4 | Ancestry-specific LD and portability. For each lead SNP, retrieve proxies (r²≥0.8 and ≥0.6) across EUR/AFR/EAS/SAS/AMR; classify portable / partially / non-portable. | LD portability summary by population. |
| 5 | Precomputed selection annotation (1000G Selection Browser, PopHumanScan). Windows ±50/100/250/500 kb. Run positive controls (LCT, EDAR, SLC24A5, DARC) to prove the pipeline recovers known signals. | Selection-evidence table with windows and caveat flags. |
| 6 | Functional / disease-biology annotation (VEP, GWAS Catalog, Open Targets, eQTL). Evidence grading with the graded matrix + red-flag penalties. | One-page reports for the 10 pilot loci; preliminary ranking. |
| 7 | Sensitivity analyses (window size, APOE/HLA exclusion, MAF bins, leave-one-resource-out) and the matched-null background prototype. | Sensitivity table; matched-null enrichment prototype. |
| 8 | Write the short pilot report + slides; produce a ranked list of 5–10 loci for follow-up. | Pilot report and ranked candidate list. |

## Weeks 9–10 (into month two): scale and present

- Scale the pipeline from 10 pilot loci to all 91 AD/ADRD loci once the workflow is proven.

- Run the matched-null enrichment across all 91 (aim for 1,000–10,000 matched sets for stable empirical p-values).

- Present the pilot to your lab and begin TOPMed/BRAVO validation for the rare-variant loci (TREM2, SORL1, ABCA7).

Mid-term success looks like A reproducible pipeline; the pilot complete and scaled to 91; genuine fluency with the core statistics and tools; data-access approvals moving; and your first lab presentation delivered.

# The next two years — long-term goals

Goal: grow Exercise 1 into real, publishable work and become genuinely expert in detecting selection. These are milestones to shape with your PI, not fixed dates — program requirements (rotations, coursework, quals) will interleave.

## Months 3–6 — From exercise to real analysis

- Finish the full 91-locus analysis with matched-null enrichment and TOPMed/BRAVO validation.

- Learn the modern toolkit hands-on: coalescent / ARG methods (Relate, tsinfer/tsdate, allele-age inference) and demographic inference (dadi, PSMC/MSMC).

- Draft a first write-up — the exercise’s ranked-hypothesis table is the seed of a methods/annotation manuscript or preprint.

## Months 6–12 — Depth and independence

- All of Us follow-up: phenotype links (lipid, immune, vascular, longevity traits) and local-ancestry analyses in admixed participants (RFMix-style methods).

- Learn the harder methods: machine-learning scans (S/HIC), polygenic-selection tests, and fine-mapping / colocalization.

- Prepare for your qualifying / candidacy exam using Exercise 1 as the worked backbone.

## Year 1–2 — Toward a thesis

- Add ancient DNA as the cleaner test of recent selection — the constructive message of Mills & Mathieson.

- Define an independent thesis question that grows out of Exercise 1 (the name implies more exercises to come). Present at a conference.

- Submit / publish your first-author paper and start a second project.

Two-year success looks like Expert-level command of selection-detection methods and their confounders; a submitted or published first-author paper; a defined thesis direction; and your qualifying exam passed.

# Skills & tools checklist

## Computational

- bcftools — filtering and querying 1000G VCFs

- PLINK2 — allele frequencies, LD, large-scale genotype handling

- scikit-allel (Python) — SFS, diversity, custom population-genetic stats

- R + LDlinkR — population-specific LD proxies and portability

- VEP / Ensembl — variant annotation and rsID → coordinate mapping

- Reproducible pipeline discipline — scripts, version control, a frozen master table

## Conceptual (in the order to learn them)

- Population-genetics logic: allele frequency, drift, Ne, Hardy–Weinberg, neutral theory

- Selection footprints: sweeps, LD, hitchhiking, hard vs. soft sweeps

- The two data views: site frequency spectrum and haplotype structure / LD decay

- The statistics by footprint: Tajima’s D, Fay & Wu’s H, iHS, XP-EHH, FST, PBS, XP-CLR, MK/HKA

- Demography as confounder; the coalescent; matched backgrounds and demographic modelling

- Recent and polygenic selection; stratification; ancient DNA

- Applied: GWAS interpretation, allele harmonization, LD portability, matched-null controls, evidence grading

- Advanced (for expertise): ARGs (Relate, tsinfer), demographic inference (dadi, PSMC/MSMC), ML scans (S/HIC), fine-mapping/colocalization, ancient DNA

# Reading list quick reference

## Read first — the three core papers

- Vitti, Grossman & Sabeti (2013), Detecting Natural Selection in Genomic Data — catalogue of footprints and statistics.

- Cheng & Steinrücken (2024), Population Genomic Scans for Natural Selection and Demography — modern methods; read twice.

- Mills & Mathieson (2022), The challenge of detecting recent natural selection in human populations — failure modes and the reviewer reflex.

## Foundational

- Coop, Population and Quantitative Genetics (free lecture notes) — best entry point for a newcomer.

- Kimura (1968) — the original neutral-theory paper.

- Hartl & Clark, Principles of Population Genetics — reference textbook.

- Nielsen (2005), Molecular signatures of natural selection.

## Project-specific

- Bellenguez et al. (2026, Nature Genetics) — your locus list; the paper the whole exercise depends on.

- Williams (1957), Pleiotropy, natural selection and the evolution of senescence — essential for your antagonistic-pleiotropy framing.

- Shi & Holtzman (2018) — innate immunity and Alzheimer’s (APOE, TREM2).

- 1000 Genomes papers (2015; Byrska-Bishop et al. 2022, high-coverage).

## Method classics (skim for intuition) + two caveat papers

- Tajima (1989), Fay & Wu (2000), Voight (2006, iHS), Sabeti (2007, XP-EHH), Weir & Cockerham (1984, FST), Chen (2010, XP-CLR/PBS).

- Give real attention to: Hernandez (2007) on ancestral-allele misidentification, and Price (2006) on population stratification — both are traps the protocol warns about.